## Table 1
ALBA Operations Calendar, January 2020-December 2020

## Table 2
BL operation bl operation Start-up Warm-up Shutdown Public & CELLS holiday | BL | BL users (external, friendly, in-house & commissioning) BL/FE/ID Commissioning & Accelerator Optimization for BLs Start up of accelerators with beam & Accelerator's Studies Warm: Linac & RF & magnets & sub-systems maintenace and optimisation Civil Engineering, Accelerators and BL maintenance with no beam, installations and upgrades
bl
M
W
Off

## Table 3
Jan 2020 Installation NOTOS FE Aug 2020 Installation XAIRA ID
Connection NOTOS FE XAIRA FE ready (?)
Installation XAIRA FE(?)

## Table 4
Weekday | JANUARY WeekDay |  | Shift M | A | N | FEBRUARY Shift Week Day M |  |  | A | N | Week | MARCH Shift M |  | A | N | Week | APRIL Shift Day M |  | A | N | MAY Week |  | Shift M | A | N | JUNE Week | Day | Shift M | A | N | JULY Week | Shift Day M |  | A | N | AUGUST WeekDay |  | Shift M | A | N | SETEMBER Shift WeekDay M |  |  | A | N | OCTOBER WeekDay |  | Shift M | A | N | NOVEMBER Shift WeekDay M |  |  | A | N | DECEMBER Shift WeekDay M |  |  | A | N
Mo | 1 | [24 empty] | 23 | 1 | M | M | M
Tu | [26 empty] | 2 | BL | BL | BL | [10 empty] | 1 |  | W | W | W | [10 empty] | 1 |  | BL | BL | BL
We | 1 |  | W | W | W | [10 empty] | 1 |  | W | W | W | [6 empty] | 3 | BL | BL | BL | 1 |  | BL | BL | BL | [5 empty] | 2 |  | W | W | W | [10 empty] | 2 |  | BL | BL | BL
Th | 2 |  | W | W | W | [10 empty] | 2 |  | W | W | W | [6 empty] | 4 | BL | BL | BL | 2 |  | BL | BL | BL | [5 empty] | 3 |  | M | M | W | 1 |  | BL | BL | BL | [5 empty] | 3 |  | BL | BL | BL
Fr | 3 |  | W | W | W | [10 empty] | 3 |  | W | W | W | 1 |  | BL | BL | BL |  | 5 | BL | BL | BL | 3 |  | BL | BL | BL | [5 empty] | 4 |  | M | M | W | 2 |  | BL | BL | BL | [5 empty] | 4 |  | BL | BL | BL
Sa | 4 |  | W | W | W | 1 |  | BL | BL | BL | [5 empty] | 4 |  | W | W | W | 2 |  | BL | BL | BL | 6 |  | BL | BL | BL | 4 |  | BL | BL | BL | 1 |  | Off | Off | Off | 5 |  | M | M | M | 3 |  | BL | BL | BL | [5 empty] | 5 |  | BL | BL | BL
Su | 5 |  | W | W | W | 2 |  | BL | BL | BL | 1 |  | W | W | W | 5 |  | W | W | W | 3 |  | BL | BL | BL | 7 |  | BL | BL | BL | 5 |  | BL | BL | BL | 2 |  | Off | Off | Off | 6 |  | M | M | M | 4 |  | M | M | M | 1 |  | BL | BL | BL | 6 |  | BL | BL | BL
Mo | 2 | 6 | W | W | W | 6 | 3 | M | M | M | 10 | 2 | M | M | M | 15 | 6 | W | W | W | 19 | 4 | M | M | M | 24 | 8 | M | M | M | 28 | 6 | M | M | M | 32 | 3 | Off | Off | Off | 37 | 7 | M | M | M | 41 | 5 | W | W | W | 45 | 2 | M | M | M | 50 | 7 | M | M | M
Tu |  | 7 | W | W | W |  | 4 | BL | BL | BL |  | 3 | BL | BL | BL |  | 7 | W | W | W |  | 5 | BL | BL | BL |  | 9 | BL | BL | BL |  | 7 | BL | BL | BL |  | 4 | Off | Off | Off |  | 8 | BL | BL | BL |  | 6 | W | W | W |  | 3 | BL | BL | BL |  | 8 | BL | BL | BL
We |  | 8 | W | W | W |  | 5 | BL | BL | BL |  | 4 | BL | BL | BL |  | 8 | W | W | W |  | 6 | BL | BL | BL |  | 10 | BL | BL | BL |  | 8 | BL | BL | BL |  | 5 | Off | Off | Off |  | 9 | BL | BL | BL |  | 7 | W | W | W |  | 4 | BL | BL | BL |  | 9 | BL | BL | BL
Th |  | 9 | W | W | W |  | 6 | BL | BL | BL |  | 5 | BL | BL | BL |  | 9 | W | W | W |  | 7 | BL | BL | BL |  | 11 | BL | BL | BL |  | 9 | BL | BL | BL |  | 6 | Off | Off | Off |  | 10 | BL | BL | BL |  | 8 | W | W | W |  | 5 | BL | BL | BL |  | 10 | BL | BL | BL
Fr |  | 10 | W | W | W |  | 7 | BL | BL | BL |  | 6 | BL | BL | BL |  | 10 | W | W | W |  | 8 | BL | BL | BL |  | 12 | BL | BL | BL |  | 10 | BL | BL | BL |  | 7 | Off | Off | Off |  | 11 | BL | BL | BL |  | 9 | W | W | W |  | 6 | BL | BL | BL |  | 11 | BL | BL | BL
Sa | 11 |  | W | W | W | 8 |  | BL | BL | BL | 7 |  | BL | BL | BL | 11 |  | W | W | W | 9 |  | BL | BL | BL | 13 |  | BL | BL | BL | 11 |  | BL | BL | BL | 8 |  | Off | Off | Off | 12 |  | BL | BL | BL | 10 |  | W | W | W | 7 |  | BL | BL | BL | 12 |  | BL | BL | BL
Su | 12 |  | W | W | W | 9 |  | BL | BL | BL | 8 |  | BL | BL | BL | 12 |  | W | W | W | 10 |  | BL | BL | BL | 14 |  | BL | BL | BL | 12 |  | BL | BL | BL | 9 |  | Off | Off | Off | 13 |  | BL | BL | BL | 11 |  | W | W | W | 8 |  | M | M | M | 13 |  | M | M | M
Mo | 3 | 13 | W | W | W | 7 | 10 | M | M | M | 11 | 9 | M | M | M | 16 | 13 | W | W | W | 20 | 11 | M | M | M | 25 | 15 | M | M | M | 29 | 13 | M | M | M | 33 | 10 | Off | Off | Off | 38 | 14 | M | M | M | 42 | 12 | W | W | W | 46 | 9 | W | W | W | 51 | 14 | BL | BL | BL
Tu |  | 14 | W | W | W |  | 11 | BL | BL | BL |  | 10 | BL | BL | BL |  | 14 | W | W | W |  | 12 | BL | BL | BL |  | 16 | BL | BL | BL |  | 14 | BL | BL | BL |  | 11 | Off | Off | Off |  | 15 | BL | BL | BL |  | 13 | M | M | M |  | 10 | W | W | W |  | 15 | BL | BL | BL
We |  | 15 | W | W | W |  | 12 | BL | BL | BL |  | 11 | BL | BL | BL |  | 15 | M | M | M |  | 13 | BL | BL | BL |  | 17 | BL | BL | BL |  | 15 | BL | BL | BL |  | 12 | Off | Off | Off |  | 16 | BL | BL | BL |  | 14 | BL | BL | BL |  | 11 | W | W | W |  | 16 | BL | BL | BL
Th |  | 16 | M | M | W |  | 13 | BL | BL | BL |  | 12 | BL | BL | BL |  | 16 | M | M | M |  | 14 | BL | BL | BL |  | 18 | BL | BL | BL |  | 16 | BL | BL | BL |  | 13 | Off | Off | Off |  | 17 | BL | BL | BL |  | 15 | BL | BL | BL |  | 12 | W | W | W |  | 17 | BL | BL | BL
Fr |  | 17 | M | M | W |  | 14 | BL | BL | BL |  | 13 | bl | bl | bl |  | 17 | BL | BL | BL |  | 15 | BL | BL | BL |  | 19 | BL | BL | BL |  | 17 | BL | BL | BL |  | 14 | Off | Off | Off |  | 18 | BL | BL | BL |  | 16 | BL | BL | BL |  | 13 | W | W | W |  | 18 | W | W | W
Sa | 18 |  | M | M | M | 15 |  | BL | BL | BL | 14 |  | bl | bl | bl | 18 |  | BL | BL | BL | 16 |  | BL | BL | BL | 20 |  | BL | BL | BL | 18 |  | BL | BL | BL | 15 |  | Off | Off | Off | 19 |  | BL | BL | BL | 17 |  | BL | BL | BL | 14 |  | W | W | W | 19 |  | W | W | W
Su | 19 |  | M | M | M | 16 |  | M | M | M | 15 |  | bl | bl | bl | 19 |  | BL | BL | BL | 17 |  | M | M | M | 21 |  | M | M | M | 19 |  | BL | BL | BL | 16 |  | Off | Off | Off | 20 |  | BL | BL | BL | 18 |  | BL | BL | BL | 15 |  | W | W | W | 20 |  | W | W | W
Mo | 4 | 20 | M | M | M | 8 | 17 | BL | BL | BL | 12 | 16 | M | M | M | 17 | 20 | M | M | M | 21 | 18 | SPR | W | W | 26 | 22 | W | W | W | 30 | 20 | M | M | M | 34 | 17 | Off | Off | Off | 39 | 21 | M | M | M | 43 | 19 | M | M | M | 47 | 16 | M | M | M | 52 | 21 | W | W | W
Tu |  | 21 | BL | BL | BL |  | 18 | BL | BL | BL |  | 17 | BL | BL | BL |  | 21 | BL | BL | BL |  | 19 | W | W | W |  | 23 | W | W | W |  | 21 | BL | BL | BL |  | 18 | Off | Off | Off |  | 22 | BL | BL | BL |  | 20 | BL | BL | BL |  | 17 | BL | BL | BL |  | 22 | W | W | W
We |  | 22 | BL | BL | BL |  | 19 | BL | BL | BL |  | 18 | BL | BL | BL |  | 22 | BL | BL | BL |  | 20 | W | W | W |  | 24 | W | W | W |  | 22 | BL | BL | BL |  | 19 | Off | Off | Off |  | 23 | BL | BL | BL |  | 21 | BL | BL | BL |  | 18 | BL | BL | BL |  | 23 | W | W | W
Th |  | 23 | BL | BL | BL |  | 20 | BL | BL | BL |  | 19 | BL | BL | BL |  | 23 | BL | BL | BL |  | 21 | W | W | W |  | 25 | W | W | W |  | 23 | BL | BL | BL |  | 20 | Off | Off | Off |  | 24 | BL | BL | BL |  | 22 | BL | BL | BL |  | 19 | BL | BL | BL |  | 24 | W | W | W
Fr |  | 24 | BL | BL | BL |  | 21 | BL | BL | BL |  | 20 | BL | BL | BL |  | 24 | BL | BL | BL |  | 22 | W | W | W |  | 26 | W | W | W |  | 24 | BL | BL | BL |  | 21 | Off | Off | Off |  | 25 | BL | BL | BL |  | 23 | BL | BL | BL |  | 20 | BL | BL | BL |  | 25 | W | W | W
Sa | 25 |  | BL | BL | BL | 22 |  | BL | BL | BL | 21 |  | BL | BL | BL | 25 |  | BL | BL | BL | 23 |  | W | W | W | 27 |  | W | W | W | 25 |  | BL | BL | BL | 22 |  | Off | Off | Off | 26 |  | bl | bl | bl | 24 |  | BL | BL | BL | 21 |  | BL | BL | BL | 26 |  | W | W | W
Su | 26 |  | BL | BL | BL | 23 |  | M | M | M | 22 |  | BL | BL | BL | 26 |  | BL | BL | BL | 24 |  | W | W | W | 28 |  | W | W | W | 26 |  | M | M | M | 23 |  | Off | Off | Off | 27 |  | bl | bl | bl | 25 |  | BL | BL | BL | 22 |  | BL | BL | BL | 27 |  | W | W | W
Mo | 5 | 27 | M | M | M | 9 | 24 | W | W | W | 13 | 23 | M | M | M | 18 | 27 | M | M | M | 22 | 25 | M | M | M | 27 | 29 | M | M | M | 31 | 27 W |  | Off | Off | 35 | 24 | W | W | W | 40 | 28 | M | M | M | 44 | 26 | M | M | M | 48 | 23 | M | M | M | 53 | 28 | W | W | W
Tu |  | 28 | BL | BL | BL |  | 25 | W | W | W |  | 24 | BL | BL | BL |  | 28 | BL | BL | BL |  | 26 | BL | BL | BL |  | 30 | M | M | M | 28 |  | Off | Off | Off |  | 25 | W | W | W |  | 29 | BL | BL | BL |  | 27 | BL | BL | BL |  | 24 | BL | BL | BL |  | 29 | W | W | W
We |  | 29 | BL | BL | BL |  | 26 | W | W | W |  | 25 | BL | BL | BL |  | 29 | BL | BL | BL |  | 27 | BL | BL | BL | [5 empty] | 29 |  | Off | Off | Off |  | 26 | W | W | W |  | 30 | BL | BL | BL |  | 28 | BL | BL | BL |  | 25 | BL | BL | BL |  | 30 | W | W | W
Th |  | 30 | BL | BL | BL |  | 27 | W | W | W |  | 26 | BL | BL | BL |  | 30 | BL | BL | BL |  | 28 | BL | BL | BL | [5 empty] | 30 |  | Off | Off | Off |  | 27 | W | W | W | [6 empty] | 29 | BL | BL | BL |  | 26 | BL | BL | BL |  | 31 | W | W | W
Fr |  | 31 | BL | BL | BL |  | 28 | W | W | W |  | 27 | BL | BL | BL | [6 empty] | 29 | BL | BL | BL | [5 empty] | 31 |  | Off | Off | Off |  | 28 | W | W | W | [6 empty] | 30 | BL | BL | BL |  | 27 | BL | BL | BL
Sa | [5 empty] | 29 |  | W | W | W | 28 |  | BL | BL | BL | [5 empty] | 30 |  | BL | BL | BL | [10 empty] | 29 |  | W | W | W | [5 empty] | 31 |  | BL | BL | BL | 28 |  | BL | BL | BL
Su | [10 empty] | 29 |  | M | M | M | [5 empty] | 31 |  | BL | BL | BL | [10 empty] | 30 |  | W | W | W | [10 empty] | 29 |  | BL | BL | BL
Mo | [10 empty] | 14 | 30 | W | W | W | [20 empty] | 36 | 31 | W | W | W | [10 empty] | 49 | 30 | M | M | M
Tu | [11 empty] | 31 | W | W | W

## Table 5
2020 versio 4.0
22/07/2019, MBM approved
8 shut downs
24 days off in August w/o public holidays
20190722_2020_calendari_v4_MBM_Approved.xlsx OP 2020 v 4.0 (sense festius)
31/07/201908:56